## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Implement NPC | 2
| Refactor to Support NPC | 2
| Add NPC to World | 0.5
| Load NPC | 3
| NPC movement | 4
| Implement Items | 2
| Refactor to Support Items | 2
| Add Items to World | 0.5
| Implement Item/NPC interaction | 5
| Load Items | 3
| Dynamic Map Generation | 15
| Estimate Totals | 39 | 0 | 0 | 0 | 0