## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
| Refactor to Support Items | 2 | 3
Pick up/Drop Item from location | Implement Items | 2 | 0.5
| Load Items | 3 | 0.5
Use item from inventory | Add Items to World | 0.5 | 1
| Refactor to Support NPC | 2 | 1
| Implement NPC | 2 | 2
| Load NPC | 3 | 2
| Add NPC to World | 0.5 | 0.5
| NPC movement (Did not implement) | 4 | 0
Interact with NPC | Implement Item/NPC interaction | 5 | 5
The system to be able to generate new maps | Implement WorldManager | 15
| Implement WorldGenerator | 0.1
| Shuffle Rooms | 0.5
| Connect Rooms | 0.1
| Estimate Totals | 39.7 | 15.5 | 0 | 0 | 0